## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE:Twitter Sentiment Analysis | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE:Prof.Anagha Aher | [6 empty] | DATE | [6 empty] | 23/10/2023
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Sumit Samanta,Shreyas Revankar,Swa Swapnil Rathod,Janvi Sharma | 11/07/2023 | 11/07/2023 | 1D | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Sumit Samanta | 18/07/2023 | 18/07/2023 | 1D | 100% | bar: WEEK 3 M to WEEK 4 F
1.3 | Discussing the project topic with the help of paper prototype. | Sumit Samanta, Shreyas Revankar,Swa Swapnil Rathod,Janvi Sharama | 18/07/2023 | 3/08/2023 | 2 | 100% | bar: WEEK 5 M to WEEK 6 F
1.4 | Designing the Graphical User Interface(GUI) | Shreyas Revankar,Swapnil Rathod | 10/08/2023 | 16/08/2023 | 1 | 100% | bar: WEEK 7 M to WEEK 8 F
1.5 | Presentation I | Sumit Samanta,Swapnil Rathod, Shreyas Revankar,Janvi Sharma | 13/09/2023 | 13/09/2023 | 1D | 100% | bar: WEEK 9 M to WEEK 9 F
2 | Project Design and Implementation
2.1 | Database Design | Sumit Samanta, Janvi Sharma | 19/09/2023 | 25/09/2023 | 7 | 100% | bar: WEEK 10 M to WEEK 10 F
2.2 | Database Connectivity of all modules | Shreyas Revankar | 26/09/2023 | 30/09/2023 | 5D | 100% | bar: WEEK 11 M to WEEK 11 F
2.3 | Integration of all modules and Report Writing | Swapnil Rathod,Janvi Sharma | 1/10/2023 | 14/10/2023 | 2 | 100%
2.4 | Presentation II | Sumit Samanta,Sw Swapnil Rathod,Shr Shreyas Revankar, Janvi Sharma | 27/10/2023 | 27/10/2023 | 1D | 100% | bar: WEEK 13 M to WEEK 14 F